## Sheet1
CSI4142 - Project W23
Phase 2- Physical design and data staging
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
high level plan | Gary Gao, Yingqi Feng, Binxuan Wu | March 10 th | March 10 th | 3 hrs | 4.5 hrs
Create database instance | Gary Gao | March 14 th | March 14 th | 2 hrs | 3 hrs
Create <building> dimension | Yingqi Feng | March 17 th | March 17 th | 0.5 hrs | 1 hrs
Create <date> dimension | Yingqi Feng | March 17 th | March 17 th | 0.5 hrs | 1 hrs
Create <house_price> dimension | Binxuan Wu | March 17 th | March 18 th | 0.5 hrs | 0.5 hrs
Create <community> dimension | Gary Gao | March 17 th | March 18 th | 0.5 hrs | 0.5 hr
Staging of fact table | Binxuan Wu | March 18 th | March 18 th | 0.5 hrs | 0.5 hrs
Staging of dimension <commnunity> | Gary Gao | March 18 th | March 18 th | 0.5 hrs | 1 hr
Staging of dimension <building> | Yingqi Feng | March 18 th | March 18 th | 0.5 hrs | 1 hr
Staging of dimension <date> | Yingqi Feng | March 18 th | March 18 th | 0.5 hrs | 0.5 hrs
Surrogate key pipeline | Binxuan Wu | March 18 th | March 21 st | 1 hr | 1 hr
Staging of fact table – including FKs and measures | Gary Gao, Yingqi Feng, Binxuan Wu | March 21 st | March 21 st | 2 hrs | 2 hrs
Data quality handling and reporting | Gary Gao, Yingqi Feng, Binxuan Wu | March 21 st | March 24 th | 1 hr | 2 hr
Others – if any