## Phase3-TeamPlanning2023
CSI4142 - Project 2023
Phase 4 - Data Mining
Teamwork - breakdown of duties | Yingqi Feng | 300077437
| Binxuan Wu | 300142301
| Gary Gao | 300124236
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Data preprocessing
Data summarisation | Yingqi and Binxuan | April 8th | April 8th | 0.3 | 0.35
.. Visualisation of attributes | Binxuan and Gary | April 8th | April 8th | 0.3 | 0.4
Data transformation | Gary and Yingqi | April 8th | April 8th | 0.3 | 0.2
.. Missing values | Yingqi and Binxuan | April 8th | April 8th | 0.3 | 0.4
.. Categorical data | Binxuan and Gary | April 8th | April 9th | 0.3 | 0.25
.. Numeric data | Gary and Yingqi | April 8th | April 9th | 0.3 | 0.4
.. Feature selection | Yingqi and Binxuan | April 8th | April 9th | 0.3 | 0.45
Data mining - Classification
Decision tree | Yingqi and Binxuan | April 11th | April 11th | 0.4 | 0.25
Gradient Boosting | Binxuan and Gary | April 11th | April 11th | 0.4 | 0.3
Random Forests | Gary and Yingqi | April 11th | April 11th | 0.4 | 0.35
Comparison of results | Yingqi and Binxuan | April 11th | April 11th | 0.4 | 0.4
Summary | Binxuan and Gary | April 11th | April 11th | 0.4 | 0.4
Anomaly detection
One-class SVM | Gary and Yingqi | April 11th | April 11th | 0.4 | 0.4
Summary | Yingqi and Binxuan | April 11th | April 11th | 0.4 | 0.25
Other tasks - please specify